| Republic of Zimbabwe |  | Bindura Rural District Council |
| --- | --- | --- |

Bindura Rural District Council

Strategic Plan 2026 - 2030

# SECTION A: Profile of the Ministry/Department/Agency (MDA)

- Foreword

​It is with immense pride and a deep sense of responsibility that I present the Bindura Rural District Council (RDC) Strategic Plan for the period 2026 to 2030. This document is more than a plan; it is our solemn commitment to the citizens of Bindura, charting a clear, inclusive, and transformative course toward local prosperity.

Our strategy is inextricably linked to the national agenda. It is a direct and vigorous response to the call of the National Development Strategy 2 (NDS2: 2026–2030), which aims to consolidate the gains made under NDS1 and accelerate our journey towards achieving an Empowered and Prosperous Upper Middle-Income Society by 2030. For Bindura RDC, this means translating national policies—from macroeconomic stability to structural transformation—into tangible improvements in infrastructure, service delivery, and livelihoods at the grassroots level.

Crucially, this plan is founded upon the principle of Devolution and Decentralisation. We are focused on localizing development, ensuring that our rich resources are harnessed efficiently to benefit our communities first. Every pillar of this strategy, from boosting local economic productivity to enhancing social services, is engineered to align with the global Sustainable Development Goals (SDGs). We commit to tackling poverty (SDG 1), ensuring good health and well-being (SDG 3), providing clean water and sanitation (SDG 6), and, most importantly for a rural district, building sustainable communities and taking urgent climate action (SDGs 11 and 13).

The next five years will be defined by rigorous implementation, transparency, and collaboration. I challenge our Council management, staff, traditional leaders, private sector partners, and every resident of Bindura to embrace this blueprint. Let us work together to build resilient infrastructure, foster an investment-friendly environment, and ensure that in Bindura, truly no one and no place is left behind.

The future of Bindura rests in our collective hands. Let us build it with purpose, diligence, and unwavering unity.

Ald Ben Tafirenyika

Bindura RDC Chairperson

- Executive Summary

Bindura Rural District Council (RDC) has developed this Strategic Plan to guide local development in line with Zimbabwe’s National Development Strategy 2 (NDS2), which emphasizes inclusive growth, sustainable service delivery, and improved livelihoods. The plan provides a roadmap for transforming Bindura RDC into a resilient, well-governed, and environmentally sustainable district that contributes meaningfully to national development goals.

The Strategic Plan is anchored on six key programmes:

### 1.  Governance and Administration

- Strengthening institutional capacity, transparency, and accountability.

- Enhancing financial management systems and revenue mobilization.

- Promoting citizen participation and stakeholder engagement in decision-making.

### 2.  Water, Sanitation, and Hygiene (WASH)

- Expanding access to safe and clean water for all communities.

- Improving sanitation infrastructure to reduce disease burden.

- Promoting hygiene education and community-led initiatives for sustainable WASH practices.

### 3.  Roads

- Upgrading and maintaining rural road networks to improve connectivity.

- Facilitating access to markets, schools, and health facilities.

- Leveraging partnerships with government and private sector for infrastructure financing.

### 4.  Social Services

- Expanding access to quality education, health, and housing.

- Supporting vulnerable groups including women, youth, and persons with disabilities.

- Promoting cultural and recreational facilities to strengthen social cohesion.

### 5.  Public Safety and Security

- Enhancing disaster preparedness and response mechanisms.

- Strengthening collaboration with law enforcement agencies to ensure community safety.

- Promoting awareness campaigns on crime prevention and road safety.

### 6.  Environmental Management and Conservation

- Promoting sustainable natural resource management and climate resilience.

- Implementing afforestation and conservation programmes to protect biodiversity.

- Mainstreaming environmental education and community participation in conservation efforts.

## Strategic Alignment with NDS2

This plan directly supports NDS2’s pillars of good governance, infrastructure development, social protection, environmental sustainability, and inclusive economic growth. By focusing on service delivery, institutional strengthening, and community empowerment, Bindura RDC aims to foster a district that is economically vibrant, socially inclusive, and environmentally sustainable.

## Conclusion

The Bindura RDC Strategic Plan is a transformative framework that positions the district as a key contributor to Zimbabwe’s national development agenda. Through effective implementation of the six programmes, the Council seeks to deliver improved livelihoods, resilient infrastructure, and sustainable growth for all residents of Bindura Rural District.

- Introduction

This Strategic Plan document was a result of collaborative effort by Council and its stakeholders. The plan precedes the Council 2019-2020 Strategic Plan that had been crafted under the guidance of the Transitional Stabilization Programme (2018-2020). Preparation of this strategic plan was informed by the new National Development Strategy 1 (NDS2) (2026-2030). The overarching goal of the NDS2 is to ensure high, accelerated, inclusive and sustainable economic growth as well as socio-economic transformation and development as the country moves “Towards a Prosperous and Empowered Upper Middle-Income Society by 2030”. This strategic plan covers period 2026 - 2030.

This strategic plan provides the strategic trajectory to position the Local authority as it seeks to become a Rural District Council with socially and economically empowered communities by 2030.This will be achieved through implementation of the following 6 programmes, Governance and Administration, Water, Sanitation and Hygiene, Social Service, Road, Public Safety and Security and lastly Natural Resources, Conservation and management. Implementation of these programmes will be underpinned by the IRBM system which promotes a culture of high performance, quality service delivery, measurement, goal clarity, continuous improvement and accountability.

- Background

Bindura RDC came into existence in 1994 as a result of the amalgamation process which saw the merging of Kubatana Bindura Rural District and Bindura Rural Council. The Council with a population of 169 841 (National Census, 2022) is located in Mashonaland Central. The current GDP per capita of the province is currently US$2,656.41 (ZIMSTAT 2024).

Bindura Rural District Council surrounds Bindura Municipality which is the provincial capital of Mashonaland Central Province. The District is gifted with skilled and well diversified human capital. It is home to the Bindura University of Science and Education, Ezekiel Guti University and Zimbabwe Open University. The major economic activities in the District are Mining and agriculture.

Mineral resources in excess of 27 types are available across the District. The District is also the proud home of the largest gold mine in the country (Freda Rebecca Gold mine) and the largest nickel mine in Southern Africa (Trojan Nick mine).The District is gifted with fertile soils and abundant rainfall and perennial rivers ideal for water harvesting for irrigation e.g., Mazowe and Pote. Areas of Investment also include Irrigation development, Mechanization of production, Dam construction, Replacement of old infrastructure, Value Addition through establishment of agro-processing plant e,g.  Honey production. Fruit Canning etc. The District is also endowed with a variety of wildlife and scenic view places that are largely unexploited, High value of cultural, wildlife and landscape assets.

- National Level Contribution:

  - National Vision:  “Towards a Prosperous and Empowered Upper Middle Income Society by 2030”

  - National Priorities the Ministry/ Agency is contributing to:

| National ref | NPA/s Name | National Key Result Area | National Tertiary Outcome/s | TOUC Reference |
| --- | --- | --- | --- | --- |
| NPA3 | Infrastructural Development and Housing | Infrastructural Development | Improved Access to Basic Infrastructure Services | 6 |
|  |  | Housing Delivery | Improved access to affordable and quality housing and social amenities | 7 |
| NPA4 | Food Security, Climate Resilience and Environmental Protection | Climate and Environmental Protection | Improved climate resilience and environmental sustainability | 10 |
| NPA7 | Regional Development and Inclusivity Through Devolution and Decentralization | Devolution and Decentralisation | Enhanced Local Governance | 23 |
|  |  |  | Improved service delivery at local level | 24 |
| NPA8 | Social Development, Gender and Social Protection | Health and Wellbeing | Improved quality of life | 27 |
| NPA10 | Good Governance, Institution Building, Peace and Security | Public Service Delivery | Enhanced Inclusive Service Delivery | 30 |

- Sectoral Level Contribution:

  - Sectoral Level

| Sector ref | Sector/s Name | Sector Key Result Area | Sector Intermediate Outcome/s | Reference |
| --- | --- | --- | --- | --- |
| NPA3: INFRASTRUCTURE DEVELOPMENT AND HOUSING DEVELOPMENT |  |  |  |  |
| SKRA 07 | Transport | Transport Infrastructure Development | Improved Connectivity | 13 |
| SKRA 08 | Water and Sanitation | Water and Sanitation Infrastructure Development | Increased access to clean and portable drinking water | 15 |
| SKRA 12 | Housing and social amenities | Housing and social amenities Development | Increased availability of affordable and modern housing | 21 |
|  |  |  | Improved access to social amenities facilities | 22 |
| NPA4:FOOD SECURITY, CLIMATE RESILIENCE AND ENVIRONMENTAL PROTECTION |  |  |  |  |
| SKRA 15 | Food Security, Climate Resilience and Environmental Management | Environmental Protection | Improved Climate Action | 25 |
| NPA 7: REGIONAL DEVELOPMENT AND INCLUSIVITY THROUGH DEVOLUTION AND DECENTRALIZATION |  |  |  |  |
| SKRA 29 SKRA 30 | Public Administration | Social Inclusion and Equity Fiscal Devolution and Resource Mobilisation Provincial Economic Plan & Implementation | Strengthened Local Governance Institutions Improved fiscal Devolution & resource mobilisation Enhanced provincial Economic planning and implementation | 45 |
| NPA 8: SOCIAL DEVELOPMENT AND SOCIAL PROTECTION |  |  |  |  |
| SKRA 31 | Health | Health provision Social Assistance, Care and Support Services | Increased Availability of Medicines | 50 |
|  |  |  | Improved access to healthcare services (primary & specialist services) | 50 |
| NPA 10: GOOD GOVERNANCE, INSTITUTION BUILDING, PEACE AND SECURITY |  |  |  |  |
| SKRA 34 | Governance | Public Service Delivery | Enhanced inclusive Governance and Accountability | 66 |
|  |  |  | Enhanced Transparency and accountability | 67 |
| SKRA 36 |  | Law and Order | Enhanced Public Safety | 70 |
| SKRA 37 |  | Disaster Risk Management | Enhanced Disaster Risk Management | 71 |

Ministry/Department/Agency Level

1.	MDA:		BINDURA RURAL DISTRICT COUNCIL

2.	MDA Vote Number:	………………………………….

3. 	MDA Vision Statement: a.	A Rural District Council with socially and economically empowered communities

by 2030.

- MDA Mission Statement: To provide quality services to communities in a transparent and professional manner through participatory and sustainable development approaches

- Core Values

- Team Work – collaborative effort towards effective and efficient service delivery to the community

- Accountability – being answerable and liable for all council processes and decisions

- Integrity-Council operations done in an honest, consistent and uncompromising adherence to strong moral principles and values

- Professionalism-timeous execution of council business in strict adherence to laid down standards

- Inclusivity – providing equal access to opportunities and resources to the community not excluding members on the grounds of gender, class and   disability.

6.Terms of Reference:

- Constitution of Zimbabwe Amendment (No. 20) Act 2013 Section 275

- Rural districts Council Act 29:13

- Programmes in the MDA and their functions

- Corporate Governance and Administration

- Resource mobilisation

- Financial management

- Asset management

- Formulate, implement and review policies.

- Provision of administration and secretarial services

- Design and implement the organizational structure of Council.

- Promote human resources development in pursuance with the council’s aims and objectives.

- Recruit council staff in terms of the RDC Act (Chapter 29:13)

- Formulate conditions of services of council staff in accordance with council resolutions.

- Design and implement performance management system.

- Carry out disciplinary measures and grievances handling procedures.

- Develop Annual Audit Plans

- Prepare internal audit reports.

- Ensure compliance to policies and procedures.

- Develop and implement a quality assurance program.

- Review of internal control systems

- Risk management

- Provision of procurement and disposal of asset services

- Water, Sanitation and Hygiene

- Provision of water, sanitation and hygiene

- Social Services

- Provision of housing and social amenities.

- Establishment of health, education and recreational facilities.

- Coordination of health and education programs

- Roads

- Infrastructure development and maintenance

- Natural Resources Conservation and Management

  - Promote sustainable environmental management

- Public safety and security

- Fire services and ambulance

- Policing services (including loss control and guarding)

- Provision of tower lights

- Provision of street lights

- State Enterprises and Parastatals, Statutory Bodies and Grant Aided Institutions under the MDA and their functions.

N/A

10. 	Environmental Scan

|  | Strengths (Internal) | Weaknesses (Internal) | Opportunities (External) | Threats (External) |
| --- | --- | --- | --- | --- |
| - Political | - Established legal mandate and structure for local governance - Commitment to devolution: RDC is the direct beneficiary and implementer of devolution. - Enabling internal policies. | - Political interference from central government or party politics in local decision making and resource allocation. | - Supportive government policies e.g. NDS2 and devolution policy - Stable Political Environment - Government Engagement and re-engagement efforts | - Political interference in administrative issues - Illegal economic sanctions - Policy inconsistence |
| - Economic | - Strong assets base. | - Low revenue collection. | - Stable exchange rate - Favourable economic policies - Ease of doing business thrust - Price stability for goods and services - Transfer grants support. | - High start-up costs - Bureaucratic processes - Poor debt rating - Exorbitant fees charged by Environmental Management Agency - Delayed and unfulfilled grants - Macroeconomic instability (e.g., high inflation, liquidity crunch) limiting residents' ability to pay rates and tariffs. - Climate change |
| - Social | - Strong communal networks and traditional leadership structures that facilitate social mobilisation. - High youth population offering potential for innovation and skills development. - Presence of social programs (health, education, and community development) supported by NGOs - Good cordial relations with stakeholder | - Limited social cohesion in rapidly urbanising areas (migration and informal settlements). - Low literacy levels in some rural communities hindering awareness programs. - High unemployment and dependency ratios - Brain drain | - Growing interest in youth empowerment and women-led social enterprises. - Expansion of community health and education initiatives. - Social media as a channel for civic engagement and feedback. - Availability of PPPs. | - Rising social inequalities due to uneven service delivery. - HIV/AIDS, drug abuse, artisanal mining and gender-based violence affecting productivity. - Cultural resistance to new governance practices |
| - Technological | - Basic ICT infrastructure in place at RDC offices. - Adoption of mobile technologies for communication and data sharing. - Uninterrupted power supply | - Limited ICT literacy among staff and community members. - Cost of ICT maintenance and dependence on external technical support. | - Availability of e-government platforms and national digitalization strategies. - Opportunities for smart village and GIS-based planning tools. - Partnerships with universities and ICT providers. - Leverage on Artificial Intelligence - Devolution drive | - Cybersecurity risks and data loss. - Technological obsolescence without regular updates. - Poor internet connectivity - Disjointed ERP systems |
| - Legal | - Qualified personnel - supporting statutes | - understaffing for enforcement - lack of garnishing powers | - Specialized skills (legal) | - policy inconsistency - political interference - land tenure insecurity |
| - Ecological | - conducive working environment - enabling environmental legal frameworks | - understaffing - Inadequate resources | - abundant natural resources - good rainfall patterns - availability of small and large dams | - negative climate change effects - environmental degradation - veldfires - limited access to safe water and sanitation |
| - Global | - Good governance | - imposition of unfunded budgets - lack of direct global links | - twinning arrangements - technological advancements - investment opportunities - Green economy (sustainable - development) - SDG alignment | - Climate change - cyber security - threats - political instability - humanitarian crises - pandemic & health issues |

11.	MDA Programmes and Outcomes:

| Prog. Ref | Programme Name | Programme Preliminary Outcome/s | Weight | Responsible Departments | Contributing MDAs/ Other Partners | Type of Contribution | Sector Intermediate Outcome Ref. | National Tertiary Outcome Ref | SDG Ref |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | - Governance and Administration | Improved corporate governance & administration | 10 | - admin - Finance - Audit | - Ministry of Finance, Economic Development & Investment Promotion - PRAZ - Ministry of Local Government &Public Works - Min of Labour - Development Partners - Association of Rural District Council | - financial support - Regulatory support - Technical & Regulatory support - technical & regulatory support - Technical & financial support - technical & regulatory support | 66,67 | 30 | 16,17 |
| 2 | - WASH | Improved water sanitation and hygiene | 20 | - Engineering - Social Services | - Ministry of Finance, Economic Development & Investment Promotion - .RIDA - Development partners eg UNICEF - Ministry of Health and Child Care - Ministry of Local Gvt - Ministry of Lands, Agriculture, Fisheries, Water and Rural Development - ZINWA - EMA - Catchment Councils | - financial support & technical support - technical support - technical & financial support - Technical & Financial support - Technical & regulatory support - Technical & regulatory support - Technical & regulatory support - Technical & regulatory support - Technical & regulatory support | 15 | 6 | 3,6 |
| 3 | Social Services | Improved access to social services | 20 | Spatial Planning Admin, HR and Social Services | Ministry of Finance, Economic Development & Investment Promotion Development Partners ie CAMFED MoHCC Min of Local Gvt &Public Works Ministry of Primary and Secondary Education ZETDC Ministry of Lands Ministry of Youth, Sports, Arts and Culture Ministry of Tourism & Hospitality Ministry of National Housing & Social Amenities Ministry of Women Affairs, Community, Small & Medium Enterprise Development in Zimbabwe | - Financial support - Technical & financial support - Technical & financial support - Technical support - Technical & regulatory support - Techncial & regulatory support - Technical & regulatory support - Technical support - Technical support - Technical support - technical support | 21,22 | 27 | - 1,3,4,5,10,11, |
| 4 | Roads | Improved road trafficability | 25 | Engineering | Ministry of Finance, Economic Development & Investment Promotion ZINARA Ministry of Transport RIDA Ministry of Local Government & Public Works | Financial support Financial & Technical support Technical support Technical support Technical support | 13 | 6 | 9,10 |
| 5 | Public Safety and emergency services | Enhanced public safety and security | 10 | Engineering Admin, HR and Social Services | Ministry of Finance, Economic Development & Investment Promotion ZRP ZETDC REA Security Companies Parks & Wildlife Developmental Partners | Financial support Technical support Technical & regulatory support Technical & regulatory support Technical support Technical support Technical support | 66,67 | 6 | 11 |
| 6 | Natural resources conservation and management | Improved natural resources conservation and management | 15 | Spatial Planning and Land Management | Ministry of Finance, Economic Development & Investment Promotion EMA Forestry commission ZRP ZINWA Parks and wildlife ARDAS Developmental Partners eg DAPP | financial support Technical & regulatory support Technical support Technical support Technical Regulatory support Technical support Technical support Technical & financial support | 25 | 10 | 9,11,12,13,14,15 |

12.	Policies Applicable for the MDA:

|  | External Policy | Programme Ref | Internal Policy | Programme Ref |
| --- | --- | --- | --- | --- |
| 1 | National water policy | 2,6 | Transport Policy | All progs |
| 2 | National Gender policy | All progs | Staff Recruitment, Promotion and Staff Development Policy | 1 |
| 3 | National employment policy | 1 | Natural resources protection by-laws | 6 |
| 4 | National HIV & AIDs policy | 1,2,3,4,5,6 | Code of Conduct (Grade 10 – 11 employees) | All progs |
| 5 | National Health Policy | All progs | Bindura RDC Code of Conduct (gr 10 – 11 employees) | All progs |
| 6 | Fiscal Policy | All progs | Council Annual Budget | All progs |
| 7 | National Housing policy | 3 | Council Resolutions | All progs |
| 8 | Land Policy | 3,6 | Strategic Plan | All progs |
| 9 | National Youth Policy | 1,3 | Council By-Laws | All progs |
| 10 | National Budget | All progs | Internal Audit charter | 1 |
| 11 | Education Policy | 3 | Bindura RDC Gender Policy | All progs |
| 12 | National Energy Policy | 1,2,5,6 | Clients Service Charter | All progs |
| 13 | SDGs | All progs | Bindura RDC HIV/AIDs Policy | All progs |
| 14 | National Environment Policy | 6 | Fire management Policy | 6 |
| 15 | Food and Nutrition Policy | 3 | Asset Management Policy | All |
| 16 | Model Building By-laws | 3 | Accounting Policy | 1 |
| 17 | National human settlement policy (Nov 2020) | 3 | Procedure Manual Policy | 1 |
| 18 | Civil Protection Act [Chapter 10:06 | 2,3,4,5 | Procurement Policy | 1 |
| 19 | Environmental Management Act [Chapter 22:19] | 6 | Gifts and Donations Policy | All progs |
| 20 | Education Act [Chapter 25:04] | 3 | Audit Charter | 1 |
| 21 | Roads Act [Chapter 13:18] | 3,4,5 | Audit committee Charter | 1 |
| 22 | Public health Act [Chapter 15:09] | 3 | SOP Payroll administration | 1 |
| 23 | Road Traffic Act [Chapter 13:11] | 3,4,5 | Performance Management Policy | 1 |
| 24 | Public Procurement and Disposal of Public Assets [Chapter 22:23] | All progs | Health and Wellness Policy | 3 |
| 25 | Public finance Management Act Chapter 22:19) | 1 | Due Diligence Policy | All progs |
| 26 | Labour Act (28:01) | 1 | Acting or Responsibility allowances policy | 1 |
| 27 | NSSA Act (17:04) | 1 |  |  |
| 28 | Traditional Leaders Act [Chapter 29:17] | 1 |  |  |
| 29 | Provincial Councils and Administration Act [Chapter 29:11] | 1 |  |  |
| 30 | Regional, Town and Country Planning Act [Chapter 29:12] | 3 |  |  |
| 31 | Shop Licences Act [Chapter 14:17] | 1 |  |  |
| 32 | Housing and Standards Control Act [Chapter 29:08] | 3 |  |  |
| 33 | Local Authorities Employees (Pension Schemes) Act [29:09] | 1 |  |  |
| 34 | Communal Lands Act [Chapter 20:04] | 1 |  |  |
| 35 | Traditional Beer Act [Chapter 14:24] | 1 |  |  |
| 36 | Stock Trespass Act [Chapter 19:14] | 6 |  |  |
| 37 | Cemeteries Act [Chapter 5:04] | 3 |  |  |
| 38 | Liquor Act [Chapter 14:12] | 1 |  |  |
| 39 | Housing and Building Act (Chapter 22:07) | 3 |  |  |
| 40 | Accounting policy and procedure manual | 1 |  |  |
| 41 | Collective Bargaining Agreement SI 87/2017 | 1 |  |  |
| 42 | Health and Safety Policy | 3 |  |  |
| 43 | National Integrity policy | 1 |  |  |
| 44 | Minimum Service Delivery Standards Indicators for Local Authorities (SI 170 of 2025 | all |  |  |

- DEMAND ANALYSIS

CLIENT NEEDS/PROBLEMS ANALYSIS: Negative situation for a client that needs to be addressed

| Direct Clients | Needs/Problems | Extent (Magnitude/seriousness) |
| --- | --- | --- |
| - Ratepayers | Needs Portable water | 37% of population |
|  | Health facilities | Chelvey , makaya , simoona , guhwa , muchapondwa (40%) |
|  | Educational facilities | Manhenga primary (100%), Rutope primary (100%) |
|  | Trafficable roads | 65% of road network |
|  | Reliable electricity | 55% of the households |
|  | Recreational Facilities | 85% |
|  | Establishment of dumpsite | 67% |
|  | Sewer Reticulation | 67% |
|  | Construction of public Toilets | 33% |
|  | Establishment of small Industries-Durawall type | 67% |
|  | Vendors Market | 2 (Manhenga, rutope, nyava, muchapondwa & Mupandira, nyanhewe) |
|  | Bus Terminus | Manhenga100% |
|  | Fuel Service Station sites | 4 (Manhenga, muchapondwa, matepatepa & Nyava) |
|  | Road Naming | 100% |
|  | Street lighting | 100% |
|  | Direction Signs | 100% |
|  | Problems |  |
|  | Water borne diseases | 5.4% |
|  | Illiteracy | 15% |
|  | Drug and substance abuse | 20% population (social service to provide) |
|  | Land pollution | 10% |
|  | Open defecation | 9% |
|  | Mugging and thefts | All 3 controlled centres |
|  | Hitchhiking | 100% |
| Farmers | Needs Trafficable roads | 65% of road network |
|  | Standard market facilities | 100% |
|  | Portable water | 37% of population |
|  | Information hubs/centres | 100% |
|  | Problems |  |
|  | Poor road network | 65% of road network |
|  | Water challenges | 5% of population |
| - Business community /Investors | Needs Business stands | 100% |
|  | Consultation and feedback before budget endorsements | 100% |
|  | Dumping sites | 50% |
|  | Problems |  |
|  | Mushroom of illegal business structures | 100% |
|  | Ratepayer Apathy | 60% |
|  | Pollution (land, water and air) | 10% |
| - Vendors | Needs Trafficable roads | 65% of road network |
|  | Standard market stalls | 9 |
|  | Various payment systems | 10% |
|  | Problems |  |
|  | Lack of market stalls | 70% |
| - Transporters | Needs |  |
|  | Trafficable Roads | 55% of road network |
|  | Problems |  |
|  | Poor road network | 70% |
| - Councillors | Needs Information | 100% |
|  | Timeous payment of allowances | 100% |
|  | Capacitation/ training | 100% |
|  | Problems |  |
|  | low uptake of technology | 40% |
| - Employees | Needs Good working conditions | 100% |
|  | Capacitation | 100% |
|  | Information | 100% |
|  | Job security | 100% |
|  | Problems |  |
|  | Late payment of salaries | 100% |

- STAKEHOLDERS ANALYSIS

| Direct Stakeholders | Demands/ Expectations | Extent (Magnitude/seriousness) |
| --- | --- | --- |
| - Ministry of Finance | compliance | 100% |
| - OPC | 100% compliance to government statutes, policies , projects and programmes | 100% |
| - Farmers | Road rehabilitation in farming areas | 80% |
| - ARDAS | - Modernised market stalls with cold rooms - Modernised stalls for livestock | 100% |
| - Business Community | - Construction of bus terminus - Pothole patching - Installation of public Lighting - Partnership between diaspora and community projects | 100% |
| - Ministry of Primary and Secondary Education | - Construction of a primary and secondary school at Manhenga and Rutope - Drilling of boreholes at Council schools - Maintenance and rehabilitation of Council educational facilities - Land for establishment of technical colleges ie resettlement area | 100% |
| - Zimbabwe Republic Police | Land for establishment of a police post at Manhenga | 100% |
| - Ministry of Health and Child Care | - Funding of health facilities and outreach programmes - Procurement of basic drugs - Safe water supply at Manhenga, Nyava and other rural communities - Completion of running projects - Proper Waste disposal - Council support and supervision of their health institutions | 100% |
| - Traditional Leaders | - Residential/ commercial stands - Roads rehabilitation / maintenance of Chiefs access roads - Solarised boreholes - Upgrading / renovation of existing of courtrooms | 60% |

- STRATEGIES, ASSUMPTIONS, RISKS AND MITIGATIONS

| Period | Strategies | Assumptions | Risks | Mitigations |
| --- | --- | --- | --- | --- |
| Programme 1: Governance and Administration- |  |  |  |  |
| Outcome: Improved corporate governance and administration |  |  |  |  |
| Budget Year | Strengthen Capacity Building | Availability of Funds | Skills flight | Improve Conditions of Service |
|  | Enhance Digitalization of operations | System compatibility | Low uptake cyber threats lack of skilled personnel | Capacity Building Improved Cyber Security Systems |
|  | Ensure compliance with laws and regulations. | Leadership Commitment | Reluctance | Integrate Compliance into The Corporate Culture. |
|  | Strengthen engagement of stakeholders | Support from the Ministry | Ratepayer apathy Operation inefficiency Erosion of public trust | Establish clear governance frameworks that promote transparency and accountability |
|  | Enhance sound financial management practices and explore innovative revenue generation strategies | Adequate support from Central government and policy frameworks | Deliberate manipulation of financial controls | Diversify revenue sources |
| 2-3 Years | Enhance sound financial management practices | Adequate support from Central government and policy frameworks | Deliberate manipulation of financial controls | Diversify revenue sources |
|  | Internal Controls Assessment. | adequate record for audit reports | conflict of interest | Prepare a robust, pre-agreed Communication Strategy for addressing findings |
|  | Enhance Investment promotion | Availability of investment promotion agencies | Changing investment climate | Continuous lobbying Creating one stop investment centre |
|  | Strengthen engagement of stakeholders | Support from the Ministry | Ratepayer apathy Operation inefficiency Erosion of public trust | Establish clear governance frameworks that promote transparency and accountability |
|  | Accelerate Re-capitalisation | Grant disbursements Availability of partners (PPPs) | Competing priorities Late grant disbursements | Engagement with all parties Continuous engagement with the parent Ministry |
|  | Engage debt collectors | Updated database | Reverse litigation | Effective communication and engagement |
| 4-5 Years | Leveraging external Specialist Services | Availability of Specialists | Privacy and security concerns Loss of control Unforeseen costs | Due diligence Consider cyber security measures Define clear service level agreements Regular monitoring and evaluation |
|  | Twinning with Local and International Partners | Availability of Partners Improved International Relations | Bottle Necks in Decision Making | Continuous Lobbying. |
|  | Full Digital integration | Buy in From Management And Staff | Cyber-Security Threats | Increased Cyber Security. |
|  | Strengthen engagement of stakeholders | Support from the Ministry | Ratepayer apathy Operation inefficiency Erosion of public trust | Establish clear governance frameworks that promote transparency and accountability |
| Period | Strategies | Assumptions | Risks | Mitigations |
| Programme 2: WASH |  |  |  |  |
| Outcome: Improved water, sanitation and hygiene |  |  |  |  |
| Budget Year | Rehabilitate existing boreholes and water points | Availability of funding | Delays in funding disbursement | Engage community leaders early to ensure buy-in- Set up local maintenance funds |
|  | Conduct community hygiene and sanitation awareness campaigns | Community participation and cooperation | Poor community ownership leading to vandalism | Partner with NGOs and local contractors for rapid implementation |
|  | Accelerate the capacitation of borehole pump minder | availability of funding | Limited technical capacity for maintenance | Partner with NGOs and local contractors for rapid implementation |
|  | Train local water point committees on maintenance | Central Government support | Poor budget performance |  |
|  | Supply and install handwashing stations in public places (schools, clinics, markets) | Availability Technical knowledge | climate change attributing to dry holes |  |
| 2 – 3yrs | Drill new boreholes | Consistent funding from donors/government | Population growth straining new facilities | Conduct hydrogeological surveys before construction |
|  | Construct scale piped water schemes through solarised borehole scheme | Availability of skilled Personnel | Water table depletion or poor water quality | Develop water safety and monitoring plans |
|  | Promote household latrine construction through subsidies or incentives. | Political stability | Weak monitoring and enforcement of hygiene standards | Strengthen partnerships with environmental and health authorities |
|  | Introduce Ward ;School; Village WASH clubs to sustain hygiene practices |  | Community by in | Continuous engaging of community |
| 4 – 5yrs | Expand water networks to underserved communities | Stable policy environment | Climate change impacts (droughts, floods) | Implement climate-resilient infrastructure |
|  | Integrate climate resilience and smart water technologies (solar pumps, rainwater harvesting) | Continued funding and stakeholder collaboration | Equipment failure and high maintenance costs | Train local technicians and establish maintenance contracts |
|  | Institutionalize WASH programs in local development plans | Technological adaptability | Policy or governance changes disrupting priorities | Develop long-term WASH policy and budget allocation framework |
| Period | Strategies | Assumptions | Risks | Mitigations |
| Programme 3: Social Services |  |  |  |  |
| Outcome: Improved access to social services |  |  |  |  |
| Budget Year | Collaboration with the communities | Willingness of community participation | Negative political interference | Community engagement |
|  | Engagement with business community & transporters | Willingness of participation by the business community and transporters | Conflicting interests Competition from informal transporters | Enforcement of road and traffic by-laws |
|  | Lobbying for timeous and full disbursement of devolution funds through ARDCZ | preparedness of the government to disburse devolution funds | competing priorities | special levies/ borrowing |
| 2 - 3 yrs | Public Private Partnership (BOT) | Favourable Council policies (ease of doing business) | Contractual complexities Negative political interference Unstable economic environment | Due diligence |
| 4 – 5yrs | application for Land bank | willingness of the government to avail the land community buy in | bureaucratic processes | continuous engagement and follow ups |
| Period | Strategies | Assumptions | Risks | Mitigations |
| Programme 4 Roads |  |  |  |  |
| Outcome: Improved road Trafficability |  |  |  |  |
| Budget Year | Prioritize grading and spot re-gravelling of critical feeder and access roads. | Adequate fuel and maintenance resources for graders. | Budget constraints delay grading works. | Engage in public-private partnerships for road maintenance. |
|  | Repair drainage structures (culverts, side drains) to prevent wash aways. | Functional equipment | Delayed disbursement of funds | Schedule works in dry season and improve drainage capacity. |
|  | Conduct condition assessment and mapping of all local roads. | Local contractors are available and affordable | Heavy rains damage roads soon after maintenance. |  |
| 2 – 3years | Upgrade key gravel roads to all-weather standard (spot surfacing or sealing). | Sufficient budget allocations through ZINARA or devolution funds. | Poor workmanship or delayed delivery by contractors. | Enforce performance-based contracts. |
|  | Introduce community-based routine maintenance programmes. | Local communities willing to participate in maintenance schemes. | Limited technical capacity in local authority. | Conduct training for local engineers and supervisors. |
|  | Improve road signage, markings, and safety measures. |  |  | Involve local stakeholders in monitoring. |
| 4 – 5years | Implement phased road surfacing for major arterial and growth-point roads. | Continued funding support from central government. | Climate impacts (flooding, erosion) damage infrastructure | Adopt resilient road designs and materials. |
|  | Establish road asset management system (database for maintenance planning). | Technical standards are consistently applied. | Escalation in construction material costs. | Secure multi-year funding commitments. |
|  | Integrate climate-resilient designs (stormwater management, erosion control). |  |  | Promote use of local materials to reduce costs. |
| Period | Strategies | Assumptions | Risks | Mitigations |
| Programme 5: Public safety and emergency services: |  |  |  |  |
| Outcome: Enhanced public safety and security: |  |  |  |  |
| Budget Year | Conduct fire risk assessments for all high-density and high-risk areas | Funding allocated in local government budgets. | Procurement delays | Streamline procurement with pre-approved supplier lists |
|  | Procure and deploy functional fire tenders to major urban and growth centres. | Cooperation from communities and private sector | Inadequate training facilities | Partner with national fire training institutions |
|  | Train and equip fire brigade personnel with modern firefighting gear | Procurement processes completed within time frame. | Limited public cooperation during awareness campaigns. | Incentivize community participation via local safety committees. |
| 2 – 3 Years | Expand fire stations to peri-urban and rural areas | Continued funding and political will | Equipment maintenance challenges | Set up maintenance contracts with suppliers. |
|  | Implement digital fire reporting and GIS-based response systems | Availability of ICT infrastructure | Technology adoption resistance | Provide digital literacy training |
|  | Introduce continuous professional development for fire and safety officers | Communities willing to volunteer. | Volunteer attrition due to lack of incentives. | Introduce small stipends or recognition for volunteers. |
| 4 – 5yrs | Establish a regional fire and disaster command centre for coordination | Policy framework remains supportive | Budget reallocation or cuts. | Secure multi-year funding commitments |
|  | Replace and upgrade aging fire tenders and communication systems. | Data systems are fully functional | Data management failures | Employ data officers in safety departments. |
|  | Enforce fire safety by-laws for all new public and private buildings. | Continuous stakeholder engagement. | Policy implementations lag. | Conduct periodic policy reviews with local and national authorities. |
| Period | Strategies | Assumptions | Risks | Mitigations |
| Programme 6 Natural resources conservation and management |  |  |  |  |
| Outcome: Improved natural resources conservation and management |  |  |  |  |
| Budget Year | Awareness campaigns in partnership with enforcement agencies | community participation | competing demands | establishment of environmental local action plans |
|  | increase environmental monitors | reduced incidences of environmental degradation activities | bribery and connivance by environmental monitors | monitoring and supervision, erection of boom gates technological advancements |
|  | strengthening enforcements, of Environmental by laws | capacity to enforce the by laws support from ZRP, Forestry Commission, EMA and community, courts | Community resistance political interference | hosting awareness campaigns continuous engagement with stakeholders |
| 2 – 3years | establish ward based environmental committees | support from stakeholders and communities | competing priorities | continuous community engagement |
| 4 – 5 years | establish Council wood lots Protect Wetlands | Support from other stakeholders and community participation | community resistance resistance due to religious beliefs insufficient resource allocation continued illegal settlements | continuous engagement with relevant stakeholders capacity building |

SECTION B: PERFORMANCE FRAMEWORK FOR THE MDA

- Programme Performance Framework

- 16.a Preliminary Outcome Performance Framework

| Ref | Outcome Description | KPI: | Measurement Criterion (time;$;rate;etc) | Baseline |  | TARGETS |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  | 2026 |  | 2027 |  | 2028 |  | 2029 |  | 2030 |  |
|  |  |  |  | Year | Value | T | ALV | T | ALV | T | ALV | T | ALV | T | ALV |
| 1 | Improved corporate governance and administration | Client satisfaction index | % | 2023 | 38 | 69 | +/-4 | 72 | 0 | 75 | +/-7 | 78 | +/-7 | 80 | 0 |
|  |  | Employee satisfaction index | % | 2023 | 52 | 69 | +/-4 | 72 | 0 | 75 | +/-7 | 78 | +/-7 | 80 | 0 |
|  |  | Financial Sustainability | % | 2023 | 59.8 | 80 | 0 | 85 | 0 | 90 | +/-9 | 95 | +/-9 | 100 | 0 |
|  |  | Statutory compliance | % | 2023 | 75 | 100 | 0 | 100 | 0 | 100 | 0 | 100 | 0 | 100 | 0 |
|  |  | Proportion of total expenditure dedicated to service delivery | % | 2023 | 70 | 70 | 0 | 70 | 0 | 70 | 0 | 70 | 0 | 70 | 0 |
|  |  | efficiency in Human resources management | % | 2023 | 54 | 75 | 0 | 77 | 0 | 80 | +/-8 | 85 | +/-8 | 90 | 0 |
|  |  | availability of Estates and development planning policies | % | 2023 | 40 | 100 | 0 | 100 | 0 | 100 | 0 | 100 | 0 | 100 | 0 |
|  |  | extent of gender mainstreaming | % | 2025 | 40 | 50 | 0 | 65 | 0 | 80 | +/-8 | 90 | +/-9 | 100 | 0 |
|  |  | Adherence to Mandatory Council Meetings and Policies | % | 2023 | 78.9 | 100 | 0 | 100 | 0 | 100 | 0 | 100 | 0 | 100 | 0 |
|  |  | Extent of Payment of Statutory Obligations | % | 2023 | 75 | 100 | 0 | 100 | 0 | 100 | 0 | 100 | 0 | 100 | 0 |
|  |  | Status of Audited Accounts | % | 2023 | 85 | 100 | 0 | 100 | 0 | 100 | 0 | 100 | 0 | 100 | 0 |
|  |  | Extent of E-governance | % | 2023 | 54 | 60 | 0 | 70 | +/-7 | 80 | +/-8 | 90 | +/-9 | 100 | 0 |
|  |  | Efficiency in Asset Management | % | 2023 | 60 | 70 | 0 | 75 | 0 | 80 | +/-8 | 90 | +/-9 | 100 | 0 |
| 02 | Improved water sanitation and hygiene | Coverage of Basic Water Supply | % | 2023 | 21.9 | 75 | 0 | 81 | 0 | 87 | +/-8 | 95 | +/-9 | 100 | 0 |
|  |  | Efficiency of Collection of Solid Waste | % | 2023 | 100 | 100 | 0 | 100 | 0 | 100 | 0 | 100 | 0 | 100 | 0 |
|  |  | Coverage of Door-to- Door Solid Waste Collection Services | % | 2023 | 80 | 100 | 0 | 100 | 0 | 100 | 0 | 100 | 0 | 100 | 0 |
|  |  | Collection Efficiency of Sanitation System | % | 2023 | 20 | 100 | 0 | 100 | 0 | 100 | 0 | 100 | 0 | 100 | 0 |
|  |  | Coverage of Toilets | % | 2023 | 100 | 100 | 0 | 100 | 0 | 100 | 0 | 100 | 0 | 100 | 0 |
|  |  | Average Per Capita Water Supply (litres/per capita/day) | litres | 2023 | 50 | 60 | 0 | 65 | 0 | 70 | +/-7 | 75 | +/-7 | 80 | 0 |
|  |  | Extent of Metering of Water Connections | % | 2023 | 0 | 100 | 0 | 100 | 0 | 100 | 0 | 100 | 0 | 100 | 0 |
|  |  | Efficiency in Meeting Water Demand | % | 2023 | 40 | 80 | 0 | 85 | 0 | 90 | +/-9 | 95 | +/-9 | 100 | 0 |
|  |  | Extent of Non-Revenue Water (NRW) | % | 2023 | 95 | 30 | 0 | 22 | 0 | 23 | +/-2 | 24 | +/-2 | 25 | 0 |
|  |  | Average Hours of Continuous Access to Water per Day (hours/day) | hrs | 2023 | 8 | 20 | 0 | 24 | 0 | 24 | +/-2 | 24 | +/-2 | 24 | 0 |
|  |  | Quality of Water Supplied | % | 2023 | 25.3 | 100 | 0 | 100 | 0 | 100 | 0 | 100 | 0 | 100 | 0 |
|  |  | Efficiency in Satisfactory Response/Reaction to Customer Complaints | % | 2023 | 75 | 95 | 0 | 96 | 0 | 97 | 0 | 98 | 0 | 100 | 0 |
|  |  | Operating Cost Recovery in Water Supply Services | % | 2023 | - | 100 | 0 | 100 | 0 | 100 | 0 | 100 | 0 | 120 | 0 |
|  |  | Efficiency in Collection of Water Supply-Related Charges | % | 2023 | - | 100 | 0 | 100 | 0 | 100 | 0 | 100 | 0 | 100 | 0 |
|  |  | Maintenance Coverage Ratio | % | 2023 | - | 20 | 0 | 20 | 0 | 20 | 0 | 20 | 0 | 20 | 0 |
|  |  | Coverage of Properties with Adequate Sanitation Services | % | 2023 | 100 | 100 | 0 | 100 | 0 | 100 | 0 | 100 | 0 | 100 | 0 |
|  |  | Collection Efficiency of Sanitation System | % | 2023 | 0 | 100 | 0 | 100 | 0 | 100 | 0 | 100 | 0 | 100 | 0 |
|  |  | Adequacy of Treatment Capacity of Sanitation System | % | 2023 | 0 | 100 | 0 | 100 | 0 | 100 | 0 | 100 | 0 | 100 | 0 |
|  |  | Quality of Treatment of Sanitation System | % | 2023 | 100 | 100 | 0 | 100 | 0 | 100 | 0 | 100 | 0 | 100 | 0 |
|  |  | Extent of Reuse and Recycling in Sanitation System | % | 2023 | 0 | 20 | 0 | 21 | 0 | 22 | +/-2 | 23 | +/-2 | 30 | 0 |
|  |  | Efficiency in Satisfactory Response/ Reaction to Customer Complaints | % | 2023 | 0 | 95 | 0 | 96 | 0 | 97 | 0 | 98 | 0 | 100 | 0 |
|  |  | Operating Cost Recovery in Sanitation Management | % | 2023 | 0 | 100 | 0 | 100 | 0 | 105 | 0 | 110 | 0 | 115 | 0 |
|  |  | Efficiency in Collection of Sanitation Charges | % | 2023 | 0 | 80 | 0 | 85 | 0 | 90 | 0 | 95 | 0 | 100 | 0 |
|  |  | Maintenance Coverage Ratio | % | 2023 | 0 | 20 | 0 | 20 | 0 | 20 | 0 | 20 | 0 | 20 | 0 |
|  |  | Proportion of Rural Homesteads with Adequate Solid Waste Disposal Facilities | % | 2023 | 100 | 100 | 0 | 100 | 0 | 100 | 0 | 100 | 0 | 100 | 0 |
|  |  | Extent of Segregation of Solid Waste | % | 2023 | 0 | 3 | 0 | 6 | 0 | 7 | 0 | 9 | 0 | 10 | 0 |
|  |  | Extent of Recovery of Solid Waste Collected | % | 2023 | 0 | 20 | 0 | 20 | 0 | 20 | 0 | 20 | 0 | 20 | 0 |
|  |  | Extent of Scientific Disposal of Waste at Landfill/ Alternative Sites | % | 2023 | 0 | 100 | 0 | 100 | 0 | 100 | 0 | 100 | 0 | 100 | 0 |
|  |  | Efficiency in Satisfactory Response/Reaction to Customer Complaints | % | 2020 | 0 | 95 | 0 | 96 | 0 | 97 | 0 | 98 | 0 | 100 | 0 |
|  |  | Operating Cost Recovery in SWM Services | % | 2023 | 0 | 100 | 0 | 100 | 0 | 105 | 0 | 110 | 0 | 115 | 0 |
|  |  | Efficiency in Collection of SWM Charges | % | 2023 | 40 | 80 | 0 | 85 | 0 | 90 | 0 | 95 | 0 | 100 | 0 |
|  |  | Maintenance Coverage Ratio | % | 2020 | 5 | 20 | 0 | 20 | 0 | 20 | 0 | 20 | 0 | 20 | 0 |
|  |  | Coverage of Receptacles | % | 2023 | 20 | 100 | 0 | 100 | 0 | 100 | 0 | 100 | 0 | 100 | 0 |
| 3 | Improved access to social services | General Health Facilities Availability (#/10,000 people) | # | 2023 | 1.6 | 1.8 | 0 | 1.85 | 0 | 1.90 | 0 | 1.95 | 0 | 2 | 0 |
|  |  | Adequacy of Primary Education Facilities (Rural - Mines, Large Estates, Rural Townships and Growth Points) | % | 2023 | 65 | 75 | 0 | 80 | 0 | 85 | 0 | 90 | 0 | 100 | 0 |
|  |  | Adequacy of Primary Education Facilities (Rural - Communal and Resettlement Areas) | % | 2023 | 65 | 75 | 0 | 80 | 0 | 85 | 0 | 90 | 0 | 100 | 0 |
|  |  | Adequacy of Community Amenities | % | 2023 | 5 | 75 | 0 | 85 | 0 | 90 | 0 | 95 | 0 | 100 | 0 |
|  |  | Adequacy of functional settlements | % | 2023 | 40 | 80 | 0 | 85 | 0 | 90 | 0 | 95 | 0 | 100 | 0 |
|  |  | Proportion of Compliant Business Premises | % | 2023 | 50 | 100 | 0 | 100 | 0 | 100 | 0 | 100 | 0 | 100 | 0 |
|  |  | Proportion of Functional Public Toilets | % | 2023 | 40 | 100 | 0 | 100 | 0 | 100 | 0 | 100 | 0 | 100 | 0 |
|  |  | Adequacy of Secondary Educational Facilities | % | 2025 | 60 | 75 | 0 | 80 | 0 | 85 | 0 | 90 | 0 | 100 | 0 |
|  |  | Extent of Urban Renewal | % | 2025 | 65 | 80 | 0 | 85 | 0 | 90 | 0 | 95 | 0 | 100 | 0 |
|  |  | Extent of Title Surveyed Properties | % | 2023 | 0 | 80 | 0 | 85 | 0 | 90 | 0 | 95 | 0 | 100 | 0 |
|  |  | Efficiency in Collection of Housing and Community Services Charges | % | 2023 | 50 | 80 | 0 | 85 | 0 | 87 | 0 | 90 | 0 | 95 | 0 |
|  |  | Maintenance Coverage Ratio | % | 2023 | 3 | 15 | 0 | 16 | 0 | 18 | 0 | 19 | 0 | 20 | 0 |
| 4 | Improved road trafficability | Coverage of Road Network | % | 2023 | 60 | 80 | 0 | 85 | 0 | 90 | 0 | 95 | 0 | 100 | 0 |
|  |  | Condition of Roads | % | 2023 | 7 | 60 | 0 | 70 | 0 | 80 | 0 | 90 | 0 | 100 | 0 |
|  |  | Adequacy of Carriageway Markings | % | 2023 | 23.8 | 40 | 0 | 50 | 0 | 65 | 0 | 75 | 0 | 100 | 0 |
|  |  | Coverage of Controlled Intersections | % | 2023 | 0 | 80 | 0 | 85 | 0 | 90 | 0 | 95 | 0 | 100 | 0 |
|  |  | Functionality of Storm water Drainage System | % | 2023 | 66.7 | 70 | 0 | 80 | 0 | 85 | 0 | 95 | 0 | 100 | 0 |
|  |  | Efficiency in Satisfactory Response/Reaction to Customer Complaints | % | 2023 | 100 | 95 | 0 | 96 | 0 | 97 | 0 | 99 | 0 | 100 | 0 |
|  |  | Roads Maintenance Coverage Ratio | % | 2023 | 4.7 | 95 | 0 | 96 | 0 | 97 | 0 | 99 | 0 | 100 | 0 |
| 5 | Enhanced public lighting and security | Coverage of Public Lighting | % | 2023 | 0 | 75 | 0 | 80 | 0 | 90 | 0 | 95 | 0 | 100 | 0 |
|  |  | Response time/reaction to emergencies (time) | hrs | 2023 | 62 | 48 | 0 | 40 | 0 | 30 | 0 | 26 | 0 | 24 | 0 |
|  |  | Emergency services preparedness level | % | 2023 | 40 | 100 | 0 | 100 | 0 | 100 | 0 | 100 | 0 | 100 | 0 |
| 6 | Improved natural resources conservation and management | Extent of Veld Fires | % | 2023 | 2.4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |
|  |  | Wetlands Sustainably Managed | % | 2023 | 22.3 | 80 | 0 | 85 | 0 | 90 | 0 | 95 | 0 | 100 | 0 |
|  |  | Extent of Land Reclaimed | % | 2023 | 57.5 | 60 | 0 | 70 | 0 | 80 | 0 | 90 | 0 | 100 | 0 |
|  |  | Extent of Forestation | % | 2023 | 22.3 | 80 | 0 | 85 | 0 | 90 | 0 | 95 | 0 | 100 | 0 |
|  |  | Adherence to Environmental Campaigns | % | 2023 | 100 | 100 | 0 | 100 | 0 | 100 | 0 | 100 | 0 | 100 | 0 |
|  |  | Extent of Beautification of Local Authority Areas | % | 2023 | 50 | 60 | 0 | 65 | 0 | 80 | 0 | 85 | 0 | 90 | 0 |
|  |  | Compliance to EIA requirements | % | 2023 | 100 | 100 | 0 | 100 | 0 | 100 | 0 | 100 | 0 | 100 | 0 |

T = Target;	ALV = Allowable Variance

Outputs Performance Framework

| No. & Prog. ref | Outputs |  | 5 year target | Measurement Criterion (time;$;rate;etc) | Baseline |  | Targets |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  |  | 2026 |  |  | 2027 |  |  |  | 2028 |  |  | 2029 |  |  |  | 2030 |  |
|  |  |  |  |  | Value | Year | T | A | AV | T |  | ALV |  | T |  | ALV | T |  | ALV |  | T | ALV |
|  |  | Programme 1: Governance and Administration |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | OUC 1 : Improved corporate governance and administration |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| OP 1.1 | Council policies formulated |  | 25 | no | 2 | 2023 | 5 |  | 0 | 5 |  | 0 |  | 5 |  | 0 | 5 |  | 0 |  | 5 | 0 |
| OP 1.2 | Stakeholder engagement programmes conducted |  | 15 | no | 3 | 2023 | 3 |  | 0 | 3 |  | 0 |  | 3 |  | 0 | 3 |  | 0 |  | 3 | 0 |
| OP 1.3 | Revenue collected |  | 100 | % | 50 | 2023 | 60 |  | +/-6 | 70 |  | +/-7 |  | 80 |  | +/-8 | 90. |  | +/-9 |  | 100 | 0 |
| OP 1.4 | Statutory obligations paid |  | 100 | % | 75 | 2023 | 100 |  | 0 | 100 |  | 0 |  | 100 |  | 0 | 100 |  | 0 |  | 100 | 0 |
| OP 1.5 | Financial statements audited |  | 5 | no | 1 | 2023 | 1 |  | 0 | 1 |  | 0 |  | 1 |  | 0 | 1 |  | 0 |  | 1 | 0 |
| OP 1.6 | Council budget produced |  | 5 | no | 1 | 2023 | 1 |  | 0 | 1 |  | 0 |  | 1 |  | 0 | 1 |  | 0 |  | 1 | 0 |
| OP 1.7 | Council systems computerised |  | 3 | % | 50% | 2023 | 60 |  | +/-6 | 70 |  | +/-7 |  | 80 |  | +/-8 | 90 |  | +/-9 |  | 100 | +/-10% |
| OP 1.8 | Statutory meetings held |  | 176 | no | 44 | 2023 | 44 |  | 0 | 44 |  | 0 |  | 44 |  | 0 | 44 |  | 0 |  | 44 | 0 |
| OP 1.9 | Council policies implemented |  | 100 | % | 100 | 2023 | 100 |  | 0 | 100 |  | 0 |  | 100 |  |  | 100 |  | 0 |  | 100 | 0 |
| OP 1.10 | Internal audit reports produced |  | 50 | no | 10 | 2023 | 10 |  | +/-1 | 10 |  | +/-1 |  | 10 |  | +/-1 | 10 |  | +/-1 |  | 10 | +/-1 |
| OP 1.11 | Goods and services procured |  | 100 | % | 50 | 2023 | 100 |  | +/-10 | 100 |  | +/-10 |  | 100 |  | +/-10 | 100 |  | +/-10 |  | 100 | +/-10 |
| OP 1.12 | Vacant posts filled |  | 13 | no | 2 | 2023 | 5 |  | 0 | 2 |  | 0 |  | 2 |  | 0 | 2 |  | 0 |  | 2 | 0 |
| OP 1.13 | Master Asset registers maintained |  | 1 | no | 1 | 2023 | 1 |  | 0 | 1 |  | 0 |  | 1 |  | 0 | 1 |  | 0 |  | 1 | 0 |
| OP 1.14 | Financial management reports produced |  | 60 | no | 12 | 2023 | 12 |  | 0 | 12 |  | 0 |  | 12 |  | 0 | 12 |  | 0 |  | 12 | 0 |
| OP 1.15 | Plant and equipment serviced |  | 55 | no | 7 | 2023 | 11 |  | 0 | 11 |  | 0 |  | 11 |  | 0 | 11 |  | 0 |  | 11 | 0 |
| OP 1.16 | Council policies reviewed |  | 5 | no | 1 | 2023 | 1 |  | 0 | 1 |  | 0 |  | 1 |  | 0 | 1 |  | 0 |  | 1 | 0 |
| OP 1.17 | Council buildings maintained |  | 50 | no | 5 | 2023 | 10 |  | +/-1 | 10 |  | +/- |  | 10 |  | +/-1 | 10 |  | +/-1 |  | 10 | +-1 |
| OP1.18 | Ward development meetings held |  | 420 | no | - | - | 84 |  | +/-8 | 84 |  | +/-8 |  | 84 |  | +/-8 | 84 |  | +/-8 |  | 84 | +/-8 |
| OP1.19 | Performance contracts signed |  | 30 | no | 6 | 2025 | 6 |  | 0 | 6 |  | 0 |  | 6 |  | 0 | 6 |  | 0 |  | 6 | 0 |
| OP1.20 | By laws formulated |  | 15 | no | 27 | 2025 | 3 |  | 0 | 3 |  | 0 |  | 3 |  | 0 | 3 |  | 0 |  | 3 | 0 |
|  |  | Programme 2: Water Sanitation and Hygiene |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | Outcome 2: Improved water, sanitation and hygiene |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| OP 2.1 | Water treatment plant constructed |  | 1 | % | 0 | 2023 | 25% |  | +/-2 | 50% |  | +/-5 |  | 75% |  | +/-7 | 100% |  | +/-10 |  | 100% | +/-10 |
| OP 2.2 | Potable water supplied (megalitres) |  | 1614 | megl | - |  | 217 |  | +/-21 | 260 |  | +/-26 |  | 312 |  | +/-31 | 375 |  | +/-37 |  | 450 | +/-45 |
| OP 2.3 | Water reticulation network/system rehabilitated |  | 8 | no | - | 2023 | 1 |  | 0 | 1 |  | 0 |  | 2 |  | 0 | 2 |  | 0 |  | 2 | 0 |
| OP 2.4 | Water reticulation network/system constructed |  | 8 | no | - | 2023 | 2 |  | 0 | 1 |  | 0 |  | 1 |  | 0 | 2 |  | 0 |  | 2 | 0 |
| OP 2.5 | Water points established (solarized borehole drilled) |  | 41 | no | 300 | 2023 | 8 |  | +/-1 | 8 |  | +/-1 |  | 8 |  | +/-1 | 8 |  | +/-1 |  | 9 | +/-1 |
| OP 2.6 | Water points/ boreholes maintained |  | 341 | no | 300 | 2023 | 68 |  | +/-6 | 68 |  | +/-6 |  | 68 |  | +/-6 | 68 |  | +/-6 |  | 69 | +/-6 |
| OP 2.7 | New properties connected |  | 21000 | no | 434 | 2023 | 4200 |  | +/-420 | 4200 |  | +/-420 |  | 4200 |  | +/-420 | 4200 |  | +/-420 |  | 4200 | +/-420 |
| OP 2.8 | Reservoirs constructed |  | 8 | no | 2 | 2023 | 1 |  | 0 | 2 |  | 0 |  | 2 |  | 0 | 1 |  | 0 |  | 2 | 0 |
| OP 2.9 | Sewer reticulation systems / network constructed |  | 8 | no | 0 | 2023 | 1 |  | 0 | 1 |  | 0 |  | 2 |  | 0 | 2 |  | 0 |  | 2 | 0 |
| OP 2.10 | Sewer treated |  | 6 | no | 0 | 2023 | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 6 | 0 |
| OP 2.11 | Sewer blockages cleared |  | 21000 | no | 0 | 2023 | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 21000 | +/-2100 |
| OP 2.12 | public Ablution facilities constructed |  | 13 | no | 3 | 2023 | 2 |  | 0 | 2 |  |  |  | 3 |  | 0 | 3 |  | 0 |  | 3 | 0 |
| OP 2.13 | ODF communities obtained |  | 162 | no | 1 | 2023 | 32 |  | +/-3 | 32 |  | +/-3 |  | 32 |  | +/-3 | 32 |  | +/-3 |  | 34 | +/-3 |
| OP 2.14 | New properties connected to sewer |  | 21000 | no | 0 | 2023 | 0 |  | 0 | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 21000 | +/-2100 |
| OP 2.14 | Waste water collected (megalitres) |  | 968.4 | megl | 0 | 2023 | 130.2 |  | ±13 | 159.6 |  | ±15 |  | 187.2 |  | ±18 | 225 |  | ±22 |  | 270 | ±27 |
| OP2.15 | Landfill constructed |  | 2 | no | 0 | 2023 | 1 |  | 0 |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 1 | 0 |
| OP 2.16 | Solid waste management equipment purchased |  | 14 | no | 0 | 2023 | 4 |  | 0 | 2 |  | 0 |  | 3 |  | 0 | 3 |  | 0 |  | 2 | 0 |
| OP 2.17 | Landfill maintained (frequency) |  | 20 | no | 0 | 2023 | 4 |  | 0 | 4 |  | 0 |  | 4 |  | 0 | 4 |  | 0 |  | 4 | 0 |
| OP 2.18 | Solid waste recycled |  | 1 | no | 0 | 2023 | 0 |  | 0 | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 1 | 0 |
|  |  | Programme 3: Social Services |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | Outcome 3: Improved social services |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| OP3.1 | Educational facilities constructed |  | 16 | No | 2 | 2023 | 4 |  | 1 | 3 |  | 0 |  | 3 |  | 0 | 3 |  | 0 |  | 3 | 1 |
| OP3.2 | Stands allocated |  | 1800 | no | 275 | 2023 | 300 |  | +/-30 | 350 |  | +/-35 |  | 350 |  | +/-35 | 400 |  | +/-40 |  | 400 | +/-40 |
| OP3.3 | Development inspections conducted |  | 3000 | no | 549 | 2023 | 500 |  | +/-50 | 650 |  | +/-65 |  | 650 |  | +/-65 | 650 |  | +/-65 |  | 550 | +/-55 |
| OP3.4 | Housing developments regularised |  | 1000 | no | - | 2023 | 200 |  | +/-20 | 200 |  | +/-20 |  | 200 |  | +/-20 | 200 |  | +/-20 |  | 200 | +/-20 |
| OP3.5 | Health facilities constructed |  | 10 | no | 2 | 2023 | 2 |  | 0 | 2 |  | 0 |  | 2 |  | 0 | 2 |  | 0 |  | 2 | 0 |
| OP3.6 | Educational facilities rehabilitated |  | 15 | no | 1 | 2023 | 3 |  | 1 | 3 |  | 1 |  | 3 |  | 1 | 3 |  | 1 |  | 3 | 1 |
| OP3.7 | Educational facilities equipped |  | 10 | no | 1 | 2023 | 2 |  | 0 | 2 |  | 0 |  | 2 |  | 0 | 2 |  | 0 |  | 2 | 0 |
| OP3.8 | Social amenities constructed |  | 5 | no | 1 | 2023 | 1 |  | 0 | 1 |  | 0 |  | 1 |  | 0 | 1 |  | 0 |  | 1 | 0 |
| OP3.9 | Social amenities maintained |  | 5 | no | 1 | 2023 | 1 |  | 0 | 1 |  | 0 |  | 1 |  | 0 | 1 |  | 0 |  | 1 | 0 |
| OP3.10 | Health facilities equipped |  | 13 | no | 1 | 2023 | 2 |  | 0 | 3 |  | 0 |  | 3 |  | 0 | 3 |  | 0 |  | 3 | 0 |
| OP3.11 | Health facilities maintained |  | 13 | no | 2 | 2023 | 2 |  | 1 | 3 |  | 0 |  | 3 |  | 0 | 3 |  | 0 |  | 3 | 0 |
| OP3.12 | Local development plan produced |  | 1 | no | New | New | 1 |  | 0 | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 |
| OP3.13 | Title surveyed centres |  | 5 | no | New | New | 1 |  | 0 | 1 |  | 0 |  | 1 |  | 0 | 1 |  | 0 |  | 1 | 0 |
|  |  | Programme 4: Roads |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | Outcome 4: Improved road trafficability |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| OP4.1 | Roads maintained |  | 1500km | km | 125 | 2023 | 300 |  | +/-30 | 300 |  | +/-30 |  | 300 |  | +/-30 | 300 |  | +/-30 |  | 300 | +/-30 |
| OP4.2 | Roads constructed |  | 100km | km | 0 | 2023 | 30 |  | +/-3 | 10 |  | +/-1 |  | 10 |  | +/-1 | 25 |  | +/-2 |  | 25 | +/-2.5 |
| OP4.3 | Roads surfaced |  | 50km | km | 0 | 2023 | 10 |  | +/-1 | 10 |  | +/-1 |  | 10 |  | +/-1 | 10 |  | +/-1 |  | 10 | +/-1 |
| OP4.4 | Bridges constructed |  | 50 | no | 3 | 2023 | 10 |  | +/-1 | 10 |  | +/-1 |  | 10 |  | +/-1 | 10 |  | +/-1 |  | 10 | +/-1 |
| OP4.5 | Bridges maintained |  | 20 | no |  |  | 4 |  | +/-1 | 4 |  | +/-1 |  | 4 |  | +/-1 | 4 |  | +/-1 |  | 4 | +/-1 |
| OP4.6 | Road furniture and facilities installed |  | 200 | no | 2 | 2023 | 40 |  | +/-4 | 40 |  | +/-4 |  | 40 |  | +/-4 | 40 |  | +/-4 |  | 40 | +/-4 |
| OP4.7 | Road furniture and facilities maintained |  | 200 | no | 0 | 2023 | 40 |  | +/-4 | 40 |  | +/-4 |  | 40 |  | +/-4 | 40 |  | +/-4 |  | 40 | +/-4 |
| OP4.8 | Road intersections upgraded |  | 20 | no | 0 | 2023 | 4 |  | 0 | 4 |  | 0 |  | 4 |  | 0 | 4 |  | 0 |  | 4 | 0 |
|  |  | Programme 5: Public safety and security |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | Outcome 5: Enhanced public safety and security |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| OP5.1 | Public lights installed |  | 100 | no | - | 2023 | 20 |  | +/-2 | 20 |  | +/-2 |  | 20 |  | +/-2 | 20 |  | +/-2 |  | 20 | +/-2 |
| OP5.2 | Awareness campaigns held |  | 50 | no | - | 2023 | 10 |  | +/-1 | 10 |  | +/-1 |  | 10 |  | +/-1 | 10 |  | +/-1 |  | 10 | +/-1 |
| OP5.3 | Properties secured |  | 10 | no | 2 | 2023 | 2 |  | 0 | 2 |  | 0 |  | 2 |  | 0 | 2 |  | 0 |  | 2 | 0 |
| OP5.4 | By-laws enforced |  | 100 | % | 60 | 2023 | 100 |  | 0 | 100 |  | 0 |  | 100 |  |  | 100 |  | 0 |  | 100 | 0 |
|  |  | Programme 6: Natural resources conservation and management |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | Outcome 6: Improved natural resources conservation and management |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| OP6.1 | Awareness campaigns conducted |  | 250 | no | 50 | 2023 | 50 |  | +/-5 | 50 |  | +/-5 |  | 50 |  | +/-5 | 50 |  | +/-5 |  | 50 | +/-5 |
| OP6.2 | Committees capacitated |  | 300 | no | 60 | 2023 | 60 |  | +/-6 | 60 |  | +/-6 |  | 60 |  | +/-6 | 60 |  | +/-6 |  | 60 | +/-6 |
| OP6.3 | Surveillance patrols conducted |  | 240 | no | 48 | 2023 | 48 |  | +/-4 | 48 |  | +/-4 |  | 48 |  | +/-4 | 48 |  | +/-4 |  | 48 | +/-4 |
| OP6.4 | Lands reclamation programs conducted |  | 25Hactares | hec | 1 | 2023 | 5 |  | +/-0.5 | 5 |  | +/-0.5 |  | 5 |  | +/-0.5 | 5 |  | +/-0.5 |  | 5 | +/-0.5 |
| OP6.5 | Wetlands protected |  | 5 | no | New | New | 1 |  | 0 | 1 |  |  | 0 | 1 | 0 |  |  | 1 | 0 | 1 |  | 0 |
| OP6.6 | clean up campaigns conducted |  | 60 | no | 12 | 2023 | 12 |  | 0 | 12 |  |  | 0 | 12 | 0 |  |  | 12 | 0 | 12 |  | 0 |
| OP6.7 | fireguards constructed |  | 25 | km | new | new | 5 |  | +/-1 | 5 |  |  | +/-1 | 5 | +/-1 |  |  | 5 | +/-1 | 5 |  | 1 |
| OP6.8 | trees planted |  | 25000 | no | 5000 | 2023 | 5000 |  | +/-500 | 5000 |  |  | +/-500 | 5000 | +/-500 |  |  | 5000 | +/-500 | 5000 |  | +/-500 |
| OP6.9 | Local environmental action plan produced |  | 1 | no | new | new | 1 |  | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |
| OP6.10 | Environment Impact Assessments conducted |  | 500 | no | 5 | 2023 | 100 |  | +/-10 |  | 100 |  | +/-10 | 100 | +/-10 |  |  | 100 | +/-10 | 100 |  | +/-0 |

T = Target	A = Actual	AV = Actual Variance		ALV = Allowable Variance

- MDA Budget

| Programme | Sub Programme |  | Programme Outputs | Budget Last Year | Budget Current Year | Budget Year 1 | Budget Year 2 | Budget Year 3 | Budget Year 4 | Budget Year 5 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Programme 1: Governance and administration | 1 |  | Council policies formulated |  |  | 287145 | 194400 | 233280 | 279936 | 335923 |
|  | 2 |  | Stakeholder engagement programs conducted |  |  | 3435020 | 256456 | 235555 | 235400 | 256000 |
|  | 4 |  | Revenue collected |  |  | 454000 | 543678 | 567834 | 678956 | 768987 |
|  | 4 |  | statutory obligations paid |  |  | 1124275.79 | 1342657 | 1452367 | 5472000 | 6578954 |
|  | 4 |  | Financial statements audited |  |  | 513000 | 513000 | 513000 | 513000 | 513000 |
|  | 4 |  | Council budget produced |  |  | 34350 | 36700 | 458769 | 467900 | 500000 |
|  | 5 |  | Council systems computerised |  |  | 64000 | 64000 | 64000 | 64000 | 64000 |
|  | 1 |  | Statutory meetings held |  |  | 56067 | 56067 | 60267 | 63567 | 66789 |
|  | 2 |  | Internal audit reports produced |  |  | 25000 | 25000 | 25000 | 25000 | 25000 |
|  | 2 |  | Goods and services procured |  |  | 15389223964 | 15389223964 | 15389223964 | 15389223964 | 15389223964 |
|  | 3 |  | Vacant posts filled |  |  | 7569000 | 6367990 | 5578968 | 5067489 | 4577790 |
|  | 3 |  | Master asset register maintained |  |  | 20000 | 20000 | 20000 | 200002 | 20000 |
|  | 4 |  | Financial management reports produced |  |  | 65789545 | 65789545 | 65789545 | 65789545 | 65789545 |
|  | 5 |  | Plant and equipment serviced |  |  | 2500045678 | 3000000000 | 3554563240 | 2600002562 | 2000076892 |
|  | 1 |  | Council policies reviewed |  |  | 25000 | 25000 | 25000 | 25000 | 25000 |
|  | 5 |  | Council buildings maintained |  |  | 15456744 | 14567455 | 17889544 | 15645634 | 56784599 |
|  | 1 |  | Ward development meetings held |  |  | 25000 | 25000 | 25000 | 25000 | 25000 |
|  | 1 |  | Performance contracts signed |  |  | 1000 | 1500 | 1500 | 2000 | 2000 |
|  | 1 |  | By laws formulated |  |  | 15000 | 18000 | 18000 | 20000 | 20000 |
| Total Programme Budget 1 |  |  |  |  |  | 17994597191.79 | 18479025912 | 19036700333 | 18083753955 | 17525606443 |
| Programme 2: Water sanitation and hygiene | 3 |  | Water treatment plant constructed |  |  | 74034800.10 | 100000000 | 100000000 | 50000000 | 45000000 |
|  | 3 |  | Portable water supplied |  |  | 65790900 | 65790900 | 65788900 | 65790900 | 62345890 |
|  | 3 |  | Water reticulation system rehabilitated |  |  | 42700000 | 42700000 | 42700000 | 42700000 | 42700000 |
|  | 3 |  | Water reticulation system constructed |  |  | 74034800.10 | 100000000 | 100000000 | 50000000 | 45000000 |
|  | 3 |  | Water points established |  |  | 50000000 | 50000000 | 50000000 | 50000000 | 50000000 |
|  | 3 |  | Water points maintained |  |  | 4500000 | 4500000 | 4500000 | 4500000 | 4500000 |
|  | 3 |  | New properties connected |  |  | 78000000 | 67000000 | 5600000 | 34578900 | 2232333 |
|  | 3 |  | Reservoirs constructed |  |  | 80999800 | 80999800 | 80999800 | 80999800 | 80999800 |
|  | 2 |  | Sewer reticulation system constructed |  |  | 150000000 | 150000000 | 150000000 | 150000000 | 150000000 |
|  | 2 |  | Sewer treated |  |  | 100000000 | 100000000 | 100000000 | 100000000 | 100000000 |
|  | 2 |  | Sewer blockages cleared |  |  | 25000000 | 25000000 | 25000000 | 25000000 | 25000000 |
|  | 2 |  | Public ablution facilities constructed |  |  | 10800000 | 10000000 | 5000000 | 5500000 | 2040000 |
|  | 2 |  | ODF communities obtained |  |  | 2400000 | 2345798 | 2345798 | 2345798 | 2345798 |
|  | 2 |  | New properties connected to sewer |  |  | 2555007 | 2555007 | 2555007 | 2555007 | 2555007 |
|  | 2 |  | Waste water collected |  |  | 2256454 | 2256454 | 2256454 | 2256454 | 2256454 |
|  | 1 |  | Landfill constructed |  |  | 900000000 | 200000000 | 360000000 | 279000000 | 164000000 |
|  | 1 |  | Solid waste management equipment purchased |  |  | 65790900 | 62666000 | 56900000 | 45678899 | 34678900 |
|  | 1 |  | Landfill maintained |  |  | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 |
|  | 1 |  | Solid waste recycled |  |  | 34000675 | 2345798 | 2345798 | 2345798 | 2345798 |
| Total Programme Budget |  |  | - |  |  | 109228091.70 | 1216214450 | 1337835895 | 1471619484.50 | 50198240.30 |
| Programme 3: Social service |  | 1 | Educational facilities constructed |  |  | 20000000 | 18000000 | 23000000 | 40000000 | 10800000 |
|  |  | 3 | Stands allocated |  |  | 5689000 | 5000000 | 4567800 | 4578789 | 5558900 |
|  |  | 3 | Development inspections conducted |  |  | 6879999 | 6577780 | 5655689 | 4567834 | 2345333 |
|  |  | 3 | Housing developments regularised |  |  | 1230045 | 1230045 | 1230045 | 1230045 | 1230045 |
|  |  | 4 | Health centre facilities constructed |  |  | 567866 | 567866 | 567866 | 567866 | 567866 |
|  |  | 1 | Educational facilities rehabilitated |  |  | 2987900 | 2987900 | 2987900 | 2987900 | 2987900 |
|  |  | 1 | Educational facilities equipped |  |  | 234778 | 234778 | 234778 | 234778 | 234778 |
|  |  | 2 | Social amenities constructed |  |  | 40000000 | 3000000 | 25000000 | 26000000 | 20000000 |
|  |  | 4 | Health facilities maintained |  |  | 345908 | 345908 | 345908 | 345908 | 345908 |
|  |  | 3 | Local development plan produced |  |  | 222490 | - | - | - | - |
|  |  | 3 | Title surveyed centres |  |  | 2345798 | 2345798 | 2345798 | 2345798 | 2345798 |
| Total Programme Budget |  |  |  |  |  | 50296165.20 | 826 825 900 | 909508490 | 1000459339.00 | 444498349.44 |
| Programme 4: Roads |  | 1 | Roads maintained |  |  | 5400000 | 5200000 | 4567866 | 6700890 | 245698.15 |
|  |  | 1 | Roads constructed |  |  | 45000000 | 35000000 | 2500000 | 2000000 | 15000000 |
|  |  | 1 | Bridges constructed |  |  | 23500000 | 21400000 | 2000000 | 4555567 | 3200000 |
|  |  | 2 | Roads furniture and facilities installed |  |  | 3545000 | 200345 | 356789 | 455567 | 356788 |
|  |  | 2 | road furniture maintained |  |  | 2828789.5 | 256700 | 256700 | 256700 | 256700 |
|  |  | 1 | bridges maintained |  |  | 5250000 | 458900 | 458900 | 458900 | 458900 |
|  |  | 2 | road intersections upgraded |  |  | 2000000 | 150000 | 170000 | 200000 | 350000 |
| Total Programme Budget |  |  |  |  |  | 87523789.50 | 66900959 | 734691054.9 | 808160160.39 | 44406530.15 |
| Programme 5: Public safety and security service | 1 |  | Awareness campaigns held |  |  | 237684 | 237684 | 237684 | 237684 | 237684 |
|  | 2 |  | Properties secured |  |  | 234600 | 400000 | 400000 | 400000 | 400000 |
|  | 2 |  | By laws enforced |  |  | 567000 | 600000 | 600000 | 600000 | 600000 |
|  | 3 |  | Street lights installed |  |  | 1500000 | 2000000 | 3000000 | 3500000 | 3000000 |
|  | 1 |  | emergency equipment procured |  |  | 2400000 | 3441316 | 3109226 | 3343916 | 202969 |
| Total Programme Budget |  |  |  |  |  | 4939284 | 6679000 | 7346910 | 8081600 | 4440653 |
| Programme 6: Natural resources conservation and management | 1 |  | Awareness campaigns conducted |  |  | 237684 | 237684 | 237684 | 237684 | 237684 |
|  | 1 |  | Committees capacitated |  |  | 240000 | 240000 | 240000 | 240000 | 240000 |
|  | 1 |  | Surveillance patrols conducted |  |  | 357000 | 357000 | 357000 | 357000 | 357000 |
|  | 1 |  | Area reclaimed |  |  | 455000 | 455000 | 3458900 | 2567988 | 1211134 |
|  | 1 |  | Land reclamation programs conducted |  |  | 3860000 | 3657877 | 3245899 | 2555678 | 1456789 |
|  | 1 |  | Wetlands protected |  |  | 135211 | 135211 | 135211 | 135211 | 135211 |
|  | 1 |  | Clean up campaigns conducted |  |  | 237684 | 237684 | 237684 | 237684 | 237684 |
|  | 1 |  | Fireguards constructed |  |  | 568900 | 568900 | 568900 | 568900 | 568900 |
|  | 1 |  | Trees planted |  |  | 500000 | 400000 | 400000 | 400000 | 400000 |
|  | 1 |  | Local environmental action plan produced |  |  | 5969311.6 | - | - | - | - |
|  | 1 |  | Environmental impact assessments conducted |  |  | 458205 | 438888 | 345678 | 245456 | 125678 |
| Total Programme Budget |  |  |  |  |  | 13018995.60 | 14567897 | 15006745 | 12056435 | 43256342 |
| TOTAL MDA BUDGET |  |  |  |  |  | 319966646646.70 | 857092584 | 2942590628 | 3239010926 | 2085056272 |

- Human Resources for the Strategic Period.

| No. | Category | Programme 1 | Programme 2 | Programme 3 | Programme 4 | Programme 5 | Programme 6 | Ministry Total Personnel Requirements By Category |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Top Management | 4 | - | 1 | 1 | - | - | 6 |
| 2 | Middle Management | 3 | 1 | 4 | 0 | 1 | 1 | 10 |
| 3 | Supervisory Management | 2 | 0 | 4 | 2 | 2 | 0 | 10 |
| 4 | Operational and Support staff | 12 | 2 | 1 | 1 | 12 | 3 | 31 |
| 5 | Total | 21 | 3 | 8 | 4 | 15 | 4 | 57 |

20. Other Resources and Projects

- Equipment and ICTs

| Materials/ Equipment /ICT | 2026 |  |  |  | 2027 |  |  |  | 2028 |  |  |  | 2029 |  |  | 2030 |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Quantity |  | Cost |  | Quantity |  | Cost |  | Quantity |  | Cost |  | Quantity |  | Cost | Quantity |  |  | Cost |
| Motor Vehicle | 7 | 32,400,000.00 |  | 5 |  | 56 500 000 |  |  |  | 165538464 |  | 6 |  | 2027400000 |  |  | 13 | 18450000 |  |  |
| Motorised Water bowser | 1 | 72,000,00.00 |  | 1 |  | 15000000 |  | 1 |  | 64000000 |  | 1 |  | 496000000 |  |  | 1 | 2400000 |  |  |
| Refuse compactor |  |  |  |  |  |  |  | 1 |  | 56000000 |  | 1 |  | 620000000 |  |  | 1 | 2400000 |  |  |
| Borehole drilling rig | 1 | 18600000 |  |  |  |  |  |  |  |  |  | 1 |  | 1860000000 |  |  | 1 | 9000000 |  |  |
| Motorised grader | 1 | 25,200,000.00 |  | 1 |  | 30000000 |  | 1 |  | 160000000 |  | 1 |  | 1860000000 |  |  | 1 | 4500000 |  |  |
| ICT upgrade | 1 | 2,700,000.00 |  | 1 |  | 6000000 |  | - |  | 8000000 |  | - |  | 973400000 |  |  | 1 | 300000 |  |  |
| laptop | 7 | 420000 |  | 6 |  | 320000 |  | 7 |  | 748000 |  | 7 |  | 56730000 |  |  | 10 | 3780000 |  |  |
| Engineering softwares (GIS, Google earth, Plex earth, Autocad ,Civil 3D,Quantity survey, Microsoft Project) | 1 | 90000 |  | 2 |  | 1,300,000.00 |  | 3 |  | 4800000 |  | 3 |  | 18600000 |  |  | 3 | 90000 |  |  |
| Computer Accessories (Harddrives, mouse, smart phones etc) | 7 | 1500000 |  | 8 |  | 2,080,000.00 |  | 1 |  | 400000 |  | 1 |  | 3100000 |  |  | 1 | 60000 |  |  |
| Desktop | 4 | 45000000 |  | 2 |  | 900000 |  | 4 |  | 1720000 |  | 4 |  | 18600000 |  |  | 6 | 153000 |  |  |
| Printers | 5 | 22000000 |  | 2 |  | 300000 |  | 6 |  | 2240000 |  | 7 |  | 28520000 |  |  | 8 | `102000 |  |  |
| Office desks | 3 | 800000 |  | 4 |  | 900000 |  | 4 |  | 1920000 |  | 4 |  | 14880000 |  |  | 2 | 45000 |  |  |
| Solar staff house | 3 | 1200000 |  | 4 |  | 10800000 |  | 5 |  | 31200000 |  | 4 |  | 161200000 |  |  | 5 | 375000 |  |  |
| Filing cabinets | 9 | 12000000 |  | 5 |  | 9000000 |  | 6 |  | 6400000 |  | 6 |  | 40920000 |  |  | 6 | 93000 |  |  |
| Fan | 10 | 150000 |  | 15 |  | 270000 |  | 10 |  | 720000 |  | 15 |  | 5580000 |  |  | 15 | 11250 |  |  |
| Survey total station | 1 | 300000 |  | 1 |  | 40000 |  | 1 |  | 8000000 |  | 1 |  | 40300000 |  |  | 1 | 195000 |  |  |
| Pneumatic roller 15ton | 1 | 2700000 |  | - |  |  |  | 1 |  | 72000000 |  | 1 |  | 310000000 |  |  | 1 | 2700000 |  |  |
| Refridgerators | 1 | 15000 |  | 1 |  | 20000 |  | 2 |  | 68000 |  | 2 |  | 52700 |  |  | 3 | 33000 |  |  |
| Heater | 10 | 3000 |  | 2 |  | 200 |  | 12 |  | 5000 |  | 12 |  | 14000 |  |  | 12 | 20000 |  |  |
| Minibus | 1 | 45000 |  | - |  |  |  | 1 |  | 16000000 |  | 1 |  | 124000000 |  |  | 1 | 1350000 |  |  |
| Boardroom chairs | 27 | 81000 |  | 27 |  | 50000 |  | 27 |  | 2016000 |  | 27 |  | 15624000 |  |  | 27 | 162000 |  |  |
| Furniture | 10 | 60000000 |  | 12 |  | 100000000 |  | 5 |  | 960000 |  | 2 |  | 53940000 |  |  | 1 | 300000 |  |  |
| Cellphones | 7 | 253000 |  | 4 |  | 200000 |  | 7 |  | 1120000 |  | 4 |  | 6200000 |  |  | 7 | 9000000 |  |  |
| Executive chairs | 4 | 54000 |  | 2 |  | 200000 |  | 3 |  | 360000 |  | 3 |  | 2790000 |  |  | 3 | 13500 |  |  |
| Server | 1 | 200000- |  |  |  |  |  | 1 |  | 4800000 |  |  |  |  |  |  | 1 | 150000 |  |  |
| OA Printer | 1 | 150000 |  | - |  |  |  | 1 |  | 4000000 |  | 1 |  | 12400000 |  |  | 1 | 60000 |  |  |
| Survey drone | 1 | 4000000 |  | 1 |  | 2000000 |  | 1 |  | 32000000 |  | 1 |  | 124000000 |  |  | 1 | 600000 |  |  |
| Excavator | 1 | 5400000 |  | - |  |  |  | 1 |  | 80000000 |  | 1 |  | 527000000 |  |  | 1 | 4200000 |  |  |
| Landfill | 1 | 900000 |  | 1 |  | 200000 |  | 3 |  | 3600000 |  | 3 |  | 27900000 |  |  | 1 | 1200000 |  |  |
| Loose tools | 96 | 3000000 |  | 96 |  | 2000000 |  | 96 |  | 2448000 |  | 96 |  | 18972000 |  |  | 126 | 164000 |  |  |
| Public solar lighting | 20 | 150000 |  | 20 |  | 200000 |  | 20 |  | 300000 |  | 20 |  | 350000 |  |  | 20 | 3000000 |  |  |
| Borehole drilling equipment | 10 | 1800000 |  | 10 |  | 2000000 |  | 10 |  | 2500000 |  | 20 |  | 620000000 |  |  | 15 | 1725000 |  |  |
| Cemetery fencing | 2 | 600000 |  | 2 |  | 800000 |  | 2 |  | 900000 |  | 2 |  | 1000000 |  |  | 2 | 600000 |  |  |
| Classroom blocks | 5 | 80000000 |  | 5 |  | 18000000 |  | 6 |  | 23000000 |  | 5 |  | 40000000 |  |  | 7 | 10800000 |  |  |
| Clinic | 2 | 4410000 |  | 2 |  | 5000000 |  | 2 |  | 5500000 |  | 2 |  | 2000000 |  |  | 1 | 1500000 |  |  |
| Vendor markets | 1 | 2010000 |  | 1 |  | 2500000 |  | 1 |  | 2600000 |  | 1 |  | 2200000 |  |  | 1 | 210000 |  |  |
| school staff houses | 2 | 4000000 |  | 2 |  | 4500000 |  | 3 |  | 35600000 |  | 3 |  | 4200000 |  |  | 4 | 4800000 |  |  |
| Bus termini | 1 | 1500000 |  | 1 |  | 2000000 |  | 1 |  | 2200000 |  | 1 |  | 4000000 |  |  | 1 | 600000 |  |  |
| Sporting facilities | 1 | 6000000 |  | 1 |  | 7000000 |  | 1 |  | 7500000 |  | 1 |  | 7600000 |  |  | 1 | 600000 |  |  |
| Water reticulation | 1 | 74034800.10 |  | 1 |  | 100000000 |  | 1 |  | 100000000 |  | 1 |  | 50000000 |  |  | 1 | 45000000 |  |  |
| Latrine toilets | 6 | 10800000 |  | 6 |  | 10000000 |  | 4 |  | 5000000 |  | 4 |  | 5500000 |  |  | 5 | 2040000 |  |  |

- Space Requirements (where applicable)

| Location | 2026 |  | 2027 |  | 2028 |  | 2029 |  | 2030 |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Quantity (m2) | Cost | Quantity (m2) | Cost | Quantity (m2) | Cost | Quantity (m2) | Cost | Quantity (m2) | Cost |
| Head Offices | 110 | $2,000,000.00 | 500 | $15000000.00 | 500 | 80000000 | 500 | 120000000 | 500 | 1600000000 |
| Project land |  |  |  |  |  |  |  |  |  |  |
| Compensation land |  |  |  |  |  |  |  |  |  |  |

- Projects for the Period

| Project Name | 2026 |  | 2027 |  | 2028 |  | 2029 |  | 2030 |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | % completion | Cost | % completion | Cost | % completion | Cost | % completion | Cost | % completion | Cost |
| Manhenga water and sewer project | 25 | 74034800 | 50 | 100000000 | 75 | 100000000 | 100 | 50000000 | 100 | 45000000 |
| Landfill establishment | 50 | 900000 | 70 | 200000 | 80 | 3600000 | 20 | 27900000 | 100 | 1200000 |
| Construction of educational facilities | 5 | 80000000 | 5 | 18000000 | 6 | 23000000 | 5 | 40000000 | 7 | 10800000 |
| Construction of health facilities | 1 | 567866 | 1 | 567866 | 1 | 567866 | 1 | 567866 | 1 | 567866 |
| Construction of sporting facilities | 1 | 6000000 | 1 | 7000000 | 1 | 7500000 | 1 | 7600000 | 1 | 600000 |
| Establishment of Pote valley city | 1 | 58880000 | 1 | 4878900 | 1 | 4980000 |  | - |  | - |
| Rehabilitation of Paradise pools | 1 | 890000 | 1 | 890000 | 1 | 890000 | 1 | 890000 | 1 | 890000 |
| Public solar lighting | 20 | 150000 | 20 | 200000 | 20 | 300000 | 20 | 350000 | 20 | 3000000 |
| Construction of bridges | 6 | 23500000 | 4 | 21400000 | 4 | 2000000 | 8 | 4555567 | 7 | 3200000 |
| Reclamation of pitsand sites | 1 | 455000 | 1 | 455000 | 1 | 3458900 | 1 | 2567988 | 1 | 1211134 |
| Title surveys | 1 | 2345798 | 1 | 2345798 | 1 | 2345798 | 1 | 2345798 | 1 | 2345798 |
| Procurement of emergency equipment | 10 | 2400000 | 12 | 3441316 | 12 | 3109226 | 12 | 3343916 | 10 | 202969 |
| Ablution facilities | 6 | 10800000 | 6 | 10000000 | 4 | 5000000 | 4 | 5500000 | 5 | 2040000 |
| Vendor markets | 1 | 2010000 | 1 | 2500000 | 1 | 2600000 | 1 | 2200000 | 1 | 210000 |

ATTENDANCE REGISTER

Workshop Participants

| Name | Sex | Designation | Contact Details |
| --- | --- | --- | --- |
| Richard Chipfuwa | M | District Development Coordinator | 0773035379 |
| Tendai Shangwa | F | Environment Committee Chairperson | 0713519988/0773581919 |
| Sharon Gutsa | F | Area Committee Chairperson | 0715039055/0771182552 |
| Eunice Hove | F | Audit Committee Chairperson | 0772209169 |
| Doesntmatter Kapondoro | M | Chief Executive Officer | 0778006259 |
| Maringe Edmore | M | Gender Committee Chairperson | 0778656533 |
| George Chigariro | M | Treasurer | 0718889900 |
| Joyce Dondo | F | Accountant | joycedondo@yahoo.com 0773996110 |
| Raith Mashavira | M | Civil Engineering Technician | 0771180761 |
| Mutsigiri Ndomupei | F | District Schools Inspector - MOPSE | mutsigirindomupei@gmai.com 0773194134 |
| Bridgette Ananiah | F | Admin,Human Resources and Community Services Officer | 0773479558 briananiah@gmail.com |
| Ben Tafirenyika | M | Council Chairperson | bentafirenyika2017@gmail.com |
| Tonderai Masango | M | Admin,Human Resources and Community Services Committee Chairperson | 0782677421 masango.tonderai@gmail.com |
| Charles Sosera | M | Vice Council Chairperson | 0773850359 |
| Kennedy Damiso | M | Finance Committee Chairperson | 0718814837 |
| Cynthia Mahommadi | F | Procurement Officer | 0777049355 procurement.bindurardc@gmail.com |
| Killian Dzangare | M | Internal Auditor | 0772286123 |
| Hari Chepate | M | Roads and Works Committee Chairperson | 0773524496 |
| Thomas Sakahuhwa | M | Planning Technician | 0773027021 |
| Ordisen Nzvere | M | Spatial Planning Committee Chairperson | 0772304034 |
| Peace Sithole | M | Assistant Admin & Human Resources Officer | 0773474899 |
| Andrew Pedzisai | M | District Administration Officer- MOHCC | 0773231825 |
| T. Hukuimwe | M | District Arex Entension Officer | 0719261968 |
| C. Mukau | M | Chairperson – Business Community | 0772907369 |
| A. Chipadze | M | Chief Chipadze | 0778974719 |
| J. Nyarumwe | M | Chief Musana | 0772696815 |
| T. Zvomuya | M | Chief Masembura | 0780503855 |
| Maynard Nyikadzino | M | District Engineer | 0718396941 |
| Clement Chindewere | M | Environmental Technician | 0772904951 |
| Chisakwa. M | M | Chief Negomo Secretary | 0773434393 |
| Chief Inspector Chahukura | M | Officer In Charge Bindura Rural Police | 0772459022 |
| Tracy Miti | F | Assistant Social Services Officer | 0772904951 |
| Mkurazhizha | F | DDO | 0773509611 |
| Mukuya Prisca Rudo | F | Office of the President and Cabinet | 0779569833 |
| Ziki Bornwell | M | MLGPW -Monitoring and Evaluation Officer | 0774066298 |
| Vimbai Chihwai | F | Administration and Human Resources Clerk | 0774821366 veechihwai@gmail.com |
| Nyaradzo Mutanda | F | Administrative Officer | 0777416101 mutanda@gmail.com |
| Clara Dandadzi | F | Public Service Facilitator | 0775020530 claradandadzi@gmail.com |
| Rumbidzai Musara | F | Public Service Facilitator | 0773901185 |
| W. Nzvaura | M | DDF- Coordinator | 0772891472 mrnzvaura@yahoo.co.uk |
| T. Mabaya | M | District Spatial Planner | 0719319442 |
| Lickel Sebele | F | Financial Advisor = MLGPW | leesebele@gmail.com |
| Prisca Taruvinga | F | Inspectorate MLGPW | ptprisca@gmail.com |